## Succession of Phases
E-Commerce Website Scheduel and Succession of Phases | [17 empty] | Matt Decker
Assignment 2
SWE6623 Software Engineering
Phase 1: Design The Website |  |  |  | Phase 2: Database Construction/Implementation |  |  |  |  | Phase 3: Testing/Debugging |  |  |  | Phase 4: Implementation
Step 1.1: Design the Individual Pages |  |  |  | Step 2.1: Design Product Database |  |  |  |  | Step 3.1: Retest All Pages for Deadlinks or Bugs |  |  |  | Step 4.1: "Go "Live"
Activity 1.1.1: Design Welcome Page |  |  |  | Activity 2.1.1: Create A Product Database with MYSQL |  |  |  |  | Activity 3.1.1: Retest All Links |  |  |  | Activity 4.1.1: Host the Website on server |  |  |  | Estimated Time Table
Activity 1.1.2: Design Product Page | [8 empty] | Activity 3.1.2: Test all photos to ensure they load | [7 empty] | Activity |  | Estimated Time (Days)
Activity 1.1.3: Design Shopping Cart Page |  |  |  |  | Step 2.2: Create Customer Database |  |  |  | Activity 3.1.3: Test webpage for proper look and dimensions |  |  |  |  | Step 4.2: Monitor for Bugs |  |  | Step 1.1: Design Webpages
Activity 1.1.4: Design Shopping Cart Page |  |  |  | Activity 2.2.1: Create A CustomerDatabase with MYSQL | [8 empty] | Activity 4.1.1: Evaluate bugs as they appear |  |  |  | Activity 1.1.1: Design Welcome Page |  | 1
Activity 1.1.5: Design Contact Me Page | [9 empty] | Step 3.2: Test Database Connection | [6 empty] | Activity 1.1.2: Design Product Page |  | 1
Activity 1.1.6: Create User Account Page | [5 empty] | Step 2.3 Link Database |  |  | Activity 3.2.1: Test "Create User Account" migration to database | [7 empty] | Activity 1.1.3: Design Shopping Cart Page |  | 1
|  |  |  | Activity 2.3.1: Link Databases to the website |  |  |  |  | Activity 3.2.1: Test product database to ensure accuracy | [7 empty] | Activity 1.1.4: Design Shopping Cart Page |  | 1
| Step 1.2: Connect Webpages | [7 empty] | Activity 3.2.1: Test accurate storage of information in database | [7 empty] | Activity 1.1.5: Design Contact Me Page |  | 1
Activity 1.2.1: Connect All Individual Pages to Home | [16 empty] | Activity 1.1.6: Create User Account Page |  | 1
Activity 1.2.2: Ensure that no bugs or dealinks appear | [16 empty] | Step 1.2: Connect Webpages
[17 empty] | Activity 1.2.1: Connect All Individual Pages to Home |  | 0.5
|  | Step 1.3: Mobile Friendly | [14 empty] | Activity 1.2.2: Ensure that no bugs or dealinks appear |  | 0.5
Activity 1.3.1: Ensure All Pages are Mobile Friendly | [16 empty] | Step 1.3: Mobile Friendly
[17 empty] | Activity 1.3.1: Ensure All Pages are Mobile Friendly |  | 1
E-Commerce Website Activity Graph | [16 empty] | Step 2.1: Design Product Database
[17 empty] | Activity 2.1.1: Create A Product Database with MYSQL |  | 5
Step 2.2: Create Customer Database
[17 empty] | Activity 2.2.1: Create A CustomerDatabase with MYSQL |  | 5
Step 2.3: Link Database
[17 empty] | Activity 2.3.1: Link Databases to the website |  | 2
Start |  | 6 Days | .5 Days |  | .5 Days |  | 1 Day |  | 10 Days |  | 2 Days | 3 Days |  | 6 Days | 1 Day |  | Step 3.1: Retest All Pages for Deadlinks or Bugs
[17 empty] | Activity 3.1.1: Retest All Links |  | 1
|  | 1.1.1 | 1.2.1 |  | 1.2.2 |  | 1.3.1 |  | 2.1.1 |  | 2.3.1 | 3.1.1 |  | 3.2.1 |  |  | Activity 3.1.2: Test all photos to ensure they load |  | 1
[17 empty] | Activity 3.1.3: Test webpage for proper look and dimensions |  | 1
|  | 1.1.2 | [6 empty] | 2.2.1 |  |  | 3.1.2 |  | 3.2.2 | 4.1.1 |  | Step 3.2: Test Database Conenction
[17 empty] | Activity 3.2.1: Test "Create User Account" migration to database |  | 2
|  | 1.1.3 | [9 empty] | 3.1.3 |  | 3.2.3 |  |  | Activity 3.2.2: Test product database to ensure accuracy |  | 2
[17 empty] | Activity 3.2.3: Test accurate storage of information in database |  | 2
|  | 1.1.4 | [5 empty] | Critical Path | [8 empty] | Step 4.1: Go Live
[8 empty] | Available Time: 40 Days | [8 empty] | Activity 4.1.1: Host the Website on server |  | 1
|  | 1.1.5 | [5 empty] | Real Time: 30 Days | [7 empty] | Finish | Step 4.2: Monitor for Bugs
[8 empty] | Slack Time: 10 Days | [8 empty] | Activity 4.1.1: Evaluate bugs as they appear |  | On Going
|  | 1.1.6 | [5 empty] | This project can be completed in the required amount of time.
|  | Notes | [9 empty] | Latest Start Time: October 15th
|  | Steps 1.1.1 through 1.1.6 can all be done concurrently by different team members | [9 empty] | Webpages are critical to the completion of this project. A delay in the creation
|  | Step 1.3.1 can be done after the completioin of the webpages while all webpages are being connected | [9 empty] | of the webpages will result in a reduction in the amount of slack time.
Steps 3.1.1 through 3.1.3 can be completed during the database creation phase if manpower supports this course of action.
Functional Requirements | [7 empty] | Non Functional Requirements
1. Website must allow customers to browes products for sale | [8 empty] | 1. Website must properly scale to mobile devices
2. Website must allow customers to create a user account | [8 empty] | 2. Website must be secure to ensure customer payment information is not compromised
3. Website must allow customers to add products to a shopping cart | [8 empty] | 3. Website must load quick and be bug free to ensure enjoyable user experience
4. Website must allow customers to place an order, view previous orders, and pay for order. | [8 empty] | 4
5. Website must store customer information in a database
State Machine Diagram
| Search Product |  | View Item |  | Add to Shopping Cart
[5 empty] | View Cart |  |  | Register Account |  | View Profile
|  |  | Continue Shopping |  | Login to Account
Checkout
Payment Method
Shipping Details
|  | Order Confirmation |  |  | Place Order